## Instructions
MHHA Hospice Checklists — Instructions & Legend
How to use | Each tab contains one checklist. Work through items in order — later phases often depend on prior ones being complete.
Checkbox column (✓) | The ☐ symbol is a visual checkbox. Click the cell and type ✓, X, or N/A to mark status. You can also insert a checkmark symbol (Insert > Symbol).
Date Completed | The yellow column (F) is where you record the completion date for each item. Format: MM/DD/YYYY.
Phase headers | Light blue rows are phase / section headers — they span all columns and are not action items.
⚠ Warning rows | Rows beginning with ⚠ contain critical compliance warnings or transition notices (such as the MI-SLS licensing system change). Read carefully before proceeding.
Regulatory References | Column D (Regulatory Reference) cites the applicable federal CFR section, Michigan statute, or other authority. Always verify current requirements at ecfr.gov, legislature.mi.gov, and michigan.gov/lara.
MI-SLS Transition | Michigan is replacing MiPLUS with a new Michigan State Licensing System (MI-SLS) launching ~August 19, 2026. No applications or change requests will be accepted after July 31, 2026. All licenses not renewed by September 1, 2026 will be CLOSED. See flagged rows in each checklist.
Adding rows | To add a new checklist item, insert a row within the checklist and copy the formatting from an adjacent row.
Sorting / Filtering | Do not sort or filter rows — the phase header rows and checklist items must remain in order.
Questions | Michigan HomeCare and Hospice Association (MHHA) — mhha.org — provides regulatory updates, education, and member support for Michigan hospice and home care providers.
Disclaimer | This checklist is an educational resource. It does not constitute legal advice. Always verify requirements with qualified healthcare legal counsel and current regulatory sources before making compliance decisions.

## Opening a Hospice Agency
Checklist 1: Opening a Michigan Hospice Agency
Michigan HomeCare and Hospice Association (MHHA) ¦ mhha.org ¦ 2026 Edition
ℹ Estimated timeline: 6–12 months from initial planning to first patient. Complete phases in order — some steps cannot begin until prior steps are finished. Enter completion dates in the yellow column.
✓ | Task / Action Required | Responsible Party | Regulatory Reference | Notes / Contacts | Date Completed
Phase 1A — Business & Corporate Formation
☐ | Determine organizational structure (nonprofit 501(c)(3), for-profit LLC, corporation, or government entity) |  | MCL § 450.2101 et seq. | Michigan LARA Corporations Division — michigan.gov/lara
☐ | File Articles of Incorporation or Articles of Organization with Michigan LARA Corporations Division |  | Michigan Business Registry | mibusinessregistry.lara.state.mi.us
☐ | Draft and adopt Bylaws or Operating Agreement |  | 42 CFR § 418.100 | Must reflect governing body authority and full legal responsibility per MCL § 333.21413(1)
☐ | File any required DBA (assumed name) with Michigan LARA |  | Michigan Business Registry | Required if operating under a name other than legal entity name — mibusinessregistry.lara.state.mi.us
☐ | Obtain Federal Employer Identification Number (EIN) from IRS |  | IRS Form SS-4 — irs.gov | Needed before opening bank accounts or applying to Medicare/Medicaid
☐ | Apply for 501(c)(3) tax exemption if nonprofit (IRS Form 1023 or 1023-EZ) |  | 26 U.S.C. § 501(c)(3) | Allow 3–6 months for IRS processing
☐ | Open business bank account and establish financial controls |  |  | Establish chart of accounts, accounting system, and signature authority
☐ | Establish governing body (board of directors): minimum 5–7 members with clinical, financial, legal, and community expertise |  | 42 CFR § 418.100; MCL § 333.21413(1) | Board assumes full legal authority — non-delegable duty under MCL § 333.21413(1)
☐ | Adopt conflict-of-interest policy; obtain annual disclosure statements from all board members |  | OIG Compliance Guidance | Best practice; required by most accreditors
☐ | Conduct initial governing body meeting; record and retain minutes |  | 42 CFR § 418.100 | Minutes reviewed by surveyors — must document substantive discussion
Phase 1B — Insurance & Risk Management
☐ | Obtain general liability insurance |  |  | Confirm coverage limits meet lender and partner requirements
☐ | Obtain professional liability (malpractice) insurance for clinical staff |  |  | Required by most nursing facility partners
☐ | Obtain workers' compensation insurance (required by Michigan law) |  | MCL § 418.101 et seq. | Michigan Workers' Disability Compensation Act
☐ | Obtain directors and officers (D&O) liability insurance |  |  | Protects board members and executive leadership
☐ | Obtain commercial auto insurance if using agency-owned vehicles
Phase 2A — Hire Core Staff
☐ | Recruit and hire Executive Director / Administrator meeting Michigan Rule R 325.45201 qualifications (Michigan health professional license OR bachelor's degree + 2 years healthcare administration experience; minimum 20 hrs/week) |  | R 325.45201 | Must designate qualified alternate for absences
☐ | Recruit and contract with Medical Director: Michigan-licensed MD or DO; list as managing employee on CMS-855A |  | 42 CFR § 418.102; CMS-855A | Board certification in Hospice & Palliative Medicine strongly preferred
☐ | Hire at least one full-time Registered Nurse (RN) with current Michigan RN license |  | R 325.45211 | Must be unencumbered; competent in hospice clinical skills
☐ | Hire or contract with Licensed Master Social Worker (LMSW) or LBSW under LMSW supervision |  | R 325.45221; 42 CFR § 418.64(c) | Michigan Board of Social Work licensure required; federal § 418.56 also allows MFT or MHC on IDG
☐ | Identify chaplain/spiritual care professional and include in IDG |  | 42 CFR § 418.64(d) | May be contracted; must be represented on every IDG
☐ | Establish on-call schedule ensuring 24/7 RN telephone availability |  | 42 CFR § 418.64(a); R 325.45211
☐ | Identify and contract hospice aides meeting 75-hour training requirement (or current state aide registry listing) |  | 42 CFR § 418.76(b) | Michigan-registered nursing home aides deemed compliant
☐ | Develop volunteer recruitment and training program; establish 5% patient care hours tracking system |  | 42 CFR § 418.78 | Volunteers must equal at least 5% of total patient care hours of paid employees and contract staff
Phase 2B — Background Checks & Licensure Verification
☐ | Register agency with Michigan Workforce Background Check (MWBC) at miltcpartnership.org; obtain LARA-issued User ID and password |  | MCL § 333.20173a / 333.20173b | Contact 1-877-718-5547 if credentials not received
☐ | Initiate MWBC fingerprint-based background checks for all direct-access employees before they begin patient care |  | MCL § 333.20173a | Use Quick Check for preliminary screening before fingerprinting
☐ | Screen all staff and Medical Director against OIG LEIE before hire; set up monthly LEIE monitoring |  | OIG LEIE — oig.hhs.gov/exclusions | Employing excluded individuals = False Claims Act liability
☐ | Verify current, unencumbered Michigan licensure for all licensed/registered personnel; document in personnel files |  | MCL § 333.21413(1)(b) | Ongoing legal obligation — not just initial hire
☐ | Establish annual competency evaluation process for all clinical disciplines |  | 42 CFR § 418.76; R 325.45201
Phase 3 — NPI & Federal Medicare Enrollment (PECOS)
☐ | Apply for organizational (Type 2) NPI through NPPES for the agency |  | nppes.cms.hhs.gov | Allow 1–10 business days; required before CMS-855A submission
☐ | Ensure Medical Director and all practitioners hold individual (Type 1) NPIs |  | nppes.cms.hhs.gov
☐ | Complete CMS-855A Medicare Enrollment Application through PECOS; disclose all owners ≥5%, all managing employees (including Medical Director); screen all against LEIE |  | pecos.cms.hhs.gov | Do NOT begin providing services until CCN is issued and enrollment is active
☐ | Complete CMS-588 EFT Authorization Agreement and submit through PECOS |  | CMS-588 | Required for Medicare payment via electronic funds transfer
☐ | Identify Medicare Administrative Contractor (MAC) for Michigan: NGS Administrators |  | cgsmedicare.com | NGS processes Medicare hospice claims for Michigan providers
☐ | Obtain CMS Certification Number (CCN) — do NOT provide services until CCN is issued and enrollment is active in PECOS |  | 42 CFR § 424.502 | Providing services before enrollment = False Claims Act violation
Phase 4 — Michigan State Hospice Licensure (LARA/BCHS)
☐ | Draft all required policies and procedures covering Michigan Administrative Rule R 325.45101–R 325.45385 compliance areas |  | R 325.45101 et seq. | See ED Guide Chapter 3.3.3 for required policy areas
☐ | ⚠ MI-SLS TRANSITION: No applications will be accepted after July 31, 2026, until MI-SLS launches (~August 19, 2026). All licenses not renewed by September 1, 2026 will be CLOSED. Submit applications before July 31, 2026. |  | LARA MI-SLS Transition Notice | Monitor michigan.gov/lara and mhha.org for MI-SLS sign-up instructions
☐ | Submit Michigan hospice license application through MI-SLS (formerly MiPLUS — milicensing.michigan.gov); include all required corporate documents, policies, and application fee |  | R 325.45111; milicensing.michigan.gov (transitioning to MI-SLS) | Fee non-refundable; confirm current amount with LARA before applying
☐ | Respond to any BCHS requests for additional information during application review |  | LARA-BSCSupport@michigan.gov — (517) 241-0092
☐ | Receive Michigan hospice license; confirm service area, effective date, and any conditions on license |  | MCL § 333.20101 et seq. | Retain original; post as required; confirm new license number in MI-SLS
Phase 5 — Michigan Medicaid Enrollment (CHAMPS)
☐ | Obtain MILogin credentials for CHAMPS access |  | milogintp.michigan.gov
☐ | Complete Michigan Medicaid provider enrollment application through CHAMPS; attach Michigan hospice license and Medicare CCN |  | michigan.gov/medicaidproviders | Contact ProviderSupport@Michigan.gov — 1-800-292-2550
☐ | Execute Electronic Funds Transfer (EFT) authorization for Medicaid payments |  | MDHHS
☐ | Confirm active Medicaid provider enrollment and obtain Medicaid Provider ID |  | CHAMPS | Required before billing any Medicaid patient days
Phase 6 — DEA, Pharmacy & Controlled Substances
☐ | Register with DEA for controlled substance authority at deadiversion.usdoj.gov |  | 21 CFR Part 1301; dea.gov | Register all locations where controlled substances will be stored
☐ | Register with Michigan MAPS (prescription monitoring program) |  | michigan.gov/maps | Required for prescribing/dispensing Schedule II–V substances
☐ | Contract with licensed hospice pharmacy (24/7 dispensing; formulary; controlled substance policies; HIPAA BAA) |  | 42 CFR § 418.106 | Ensure comfort kit protocols are addressed in pharmacy contract
☐ | Develop controlled substance policies: comfort kits, medication log, inventory, disposal per 21 CFR § 1317 |  | 42 CFR § 418.74
Phase 7A — EMR/EHR & Technology
☐ | Select and implement EMR/EHR certified to support HOPE data collection and iQIES submission (required effective 10/1/2025) |  | 42 CFR § 418.104; CMS HQRP | Contact iQIES Support: 1-800-339-9313; confirm HOPE-readiness with vendor
☐ | Configure EMR to capture all 42 CFR § 418.54 comprehensive assessment domains and HOPE data elements |  | 42 CFR § 418.54; HOPE Guidance Manual
☐ | Implement HIPAA Security Rule safeguards: access controls, encryption, audit logs, mobile device management |  | 45 CFR Parts 160, 164 | Execute HIPAA BAA with EMR vendor and all vendors receiving PHI
☐ | Obtain and implement cybersecurity and data breach response plan |  | 45 CFR § 164.530 | HIPAA breach notification: 60 days to notify affected individuals and HHS
Phase 7B — Policies, Procedures & Compliance Program
☐ | Adopt Corporate Compliance Program per OIG 7-element framework; designate Compliance Officer |  | OIG Compliance Guidance for Hospices | oig.hhs.gov/compliance/compliance-guidance
☐ | Develop Emergency Preparedness Plan with all 4 required elements: Plan, Policies, Communication Plan, Training/Testing |  | 42 CFR § 418.113 | Coordinate with Michigan EMHSD: michigan.gov/msp/divisions/emhsd
☐ | Develop Infection Control Program: standard precautions, surveillance, reportable disease reporting per MCL § 333.5111 |  | 42 CFR § 418.60; MCL § 333.5111
☐ | Develop QAPI program: committee charter, performance indicators, data collection tools, PIP methodology |  | 42 CFR § 418.58 | Present to governing board at first post-opening meeting
☐ | Execute HIPAA Business Associate Agreements (BAAs) with all vendors receiving PHI |  | 45 CFR § 164.504(e)
Phase 7C — Partner Facility Agreements
☐ | Execute written agreements with GIP and IRC inpatient facilities (hospital or skilled nursing facility) |  | 42 CFR § 418.108 | GIP/IRC facilities must be Medicare-certified
☐ | Execute written agreements with all nursing facilities where patients will reside (room and board; coordination; joint POC) |  | 42 CFR § 418.112 | Agreement must delineate hospice vs. NF responsibilities
☐ | Execute written agreements with DME vendors, ambulance services, and other contracted service providers |  | 42 CFR § 418.100 | All arranged services require written agreements
Phase 8 — Certification Survey (CMS/BCHS or Accreditor)
☐ | Choose survey pathway: CMS/BCHS standard survey OR accreditation (CHAP — chapinc.org; ACHC — achc.org; TJC — jointcommission.org) |  | 42 CFR § 488.1 et seq. | Accreditation costs $3,000–$15,000 but provides compliance and marketing benefits
☐ | Prepare all survey-readiness documents per MHHA Survey Readiness Checklist (see ED Guide Chapter 2.4.1) |  | CMS State Operations Manual, Appendix M | Surveys are unannounced — maintain documents continuously
☐ | Conduct internal mock survey or pre-survey audit using CMS Appendix M Interpretive Guidelines |  | CMS Appendix M — Hospice | Available at cms.gov — search 'Appendix M Hospice Interpretive Guidelines'
☐ | Respond to Statement of Deficiencies (Form 2567) within 10 calendar days with Plan of Correction if deficiencies cited |  | 42 CFR § 488.325 | Describe corrective actions already taken — not future plans
☐ | Receive CMS compliance determination; confirm CCN is active in PECOS before accepting first patient |  | pecos.cms.hhs.gov
Phase 9 — HQRP & HOPE Tool Registration
☐ | Register for CMS HARP (Healthcare Provider and Resources Portal) account at harp.cms.gov — required for iQIES access |  | harp.cms.gov | Contact iQIES Support: 1-800-339-9313
☐ | Complete HOPE tool training (5-part CMS self-paced series at cms.gov/medicare/quality/hospice/hope) |  | 42 CFR § 418.58; CMS HQRP | Failure to comply with HQRP = 2% Annual Payment Update reduction
☐ | Confirm EMR/EHR HOPE data export functionality is tested and validated in iQIES |  | CMS HOPE Validation Utility Tool (VUT) | All new admissions 10/1/2025+ require HOPE records (not HIS)
☐ | Train all clinical staff on HOPE assessment completion at each required timepoint (Admission, HUV1, HUV2, Discharge, SFV) |  | HOPE Guidance Manual v1.02 | Symptom Follow-up Visit (SFV) required within 2 days of moderate-severe symptoms
Phase 10 — Pre-Launch Final Checks
☐ | Confirm Michigan hospice license is active, CCN is issued, and Medicaid enrollment is active in CHAMPS — ALL THREE must be active before accepting first patient |  | MCL § 333.20165; 42 CFR § 424.502 | Do not skip this confirmation
☐ | Post required notices in agency office: patient rights, nondiscrimination notices, state agency hotline contact |  | 42 CFR § 418.52
☐ | Conduct initial QAPI committee meeting; establish baseline quality indicator tracking |  | 42 CFR § 418.58
☐ | Conduct Emergency Preparedness tabletop exercise; document training for all staff |  | 42 CFR § 418.113 | Annual exercise required; document before first patient
☐ | Confirm 24/7 RN on-call coverage is operational; test on-call communication system |  | 42 CFR § 418.64(a)
☐ | Contact Michigan HomeCare and Hospice Association (MHHA) to establish membership |  | mhha.org | MHHA provides regulatory alerts, education, and peer networking for Michigan hospice and home care providers
☐ | File Notice of Election (NOE) with NGS Administrators within 5 calendar days of first patient's hospice election |  | 42 CFR § 418.24(e); cgsmedicare.com | Late NOE = Medicare will not pay for gap period — provider liability

## Opening a Hospice Residence
Checklist 2: Opening a Michigan Hospice Residence
Michigan HomeCare and Hospice Association (MHHA) ¦ mhha.org ¦ 2026 Edition
ℹ This checklist assumes your hospice agency is already licensed and operating. Estimated timeline: 9–18 months from planning to first patient, AFTER the mandatory 2-year precondition is met. Engage healthcare legal counsel, a healthcare architect, and a fire/life safety consultant early.
⚠ CRITICAL — MCL § 333.21413(2): Applicant must have been licensed as a hospice AND in compliance with 42 CFR Part 418 for not less than 2 years immediately before applying for residence licensure. This is a non-waivable statutory requirement. Do not invest in a residence facility before verifying your eligibility date with BCHS.
✓ | Task / Action Required | Responsible Party | Regulatory Reference | Notes / Contacts | Date Completed
Phase 1 — Eligibility Verification & Planning
☐ | Verify continuous hospice licensure for not less than 2 years AND compliance with 42 CFR Part 418 throughout that period |  | MCL § 333.21413(2) | Contact BCHS to confirm eligibility date: (517) 241-0092
☐ | Confirm no outstanding unresolved survey deficiencies that could affect eligibility |  | MCL § 333.21413(2) | Major unresolved deficiency during the 2-year period may disqualify application
☐ | Determine residence model: home-care level only, or both home care and inpatient care at same location |  | MCL § 333.21413(2) | GIP-level care requires compliance with 42 CFR § 418.100 and § 418.110
☐ | Determine number of beds; select and evaluate potential facility location |  | R 325.45301 et seq. | Minimum room sizes and physical plant requirements apply — consult BCHS
☐ | Engage architect experienced in Michigan healthcare facility licensure and NFPA 101 Life Safety Code compliance |  | NFPA 101; MCL § 333.21413(3)(c) | Design must meet BCHS physical environment requirements AND CMS Life Safety Code
☐ | Develop financial pro forma (startup costs, operating costs, projected census, payor mix) |  |  | Residences require significant capital investment — secure financing before proceeding
☐ | Notify LARA/BCHS of intent to apply; request pre-application consultation |  | (517) 241-0092 — LARA-BSCSupport@michigan.gov | Pre-application consultation prevents costly facility design or documentation mistakes
Phase 2A — Physical Environment Requirements (MCL § 333.21413(3))
☐ | Design and equip private or semi-private patient rooms meeting BCHS minimum square footage requirements |  | R 325.45301 et seq. | Contact BCHS for current minimum room size requirements
☐ | Design homelike décor throughout patient care areas; ensure comfort and dignity per MCL § 333.21413(3)(e) |  | MCL § 333.21413(3)(e) | Physical space must be designed with patient dignity and family visitation in mind
☐ | Design and equip common living areas accessible to patients and families |  | R 325.45301 et seq.
☐ | Design accessible bathrooms meeting ADA and BCHS requirements |  | R 325.45301 et seq.; ADA
☐ | Include kitchen or kitchenette space accessible to families and staff for meal preparation |  | MCL § 333.21413(3)(g); 42 CFR § 418.100(j) | Individualized meal service plans required; consult dietary counselor
☐ | Include outdoor space accessible to patients (weather permitting) |  | R 325.45301 et seq.
☐ | Install CMS/BCHS-approved nurse call device in EVERY patient room — within patient reach at all times |  | MCL § 333.21413(3)(d) | Obtain BCHS approval of specific device before installation
Phase 2B — Fire & Life Safety (Two Separate Processes — both required)
☐ | Engage licensed fire safety consultant to assess compliance with NFPA 101 Life Safety Code as adopted in Michigan |  | MCL § 333.21413(3)(c); NFPA 101 | BFS/local approval AND CMS/LSC compliance are SEPARATE processes — both required
☐ | Schedule and complete Michigan Bureau of Fire Services (BFS) inspection; obtain BFS fire safety approval before opening |  | MCL § 333.21413(3)(c); MCL § 20156 | Contact BFS through michigan.gov/lara; local fire authority having jurisdiction may also inspect
☐ | Complete CMS Life Safety Code (LSC) survey compliance — separate from BFS; coordinate with BCHS for CMS/LSC inspection scheduling |  | 42 CFR § 418.110(c); NFPA 101 | CMS/LSC inspectors are separate from BFS — both have distinct follow-up documentation requirements
☐ | Install all required fire safety equipment: sprinkler system, smoke detectors, fire alarm, emergency lighting, exit signs, fire extinguishers |  | NFPA 101 | All systems must pass inspection before first patient
☐ | Develop fire evacuation plan specific to the hospice residence and patient population; post in all required locations |  | NFPA 101; 42 CFR § 418.113 | Plan must account for mobility-impaired patients
Phase 2C — Food Service Setup
☐ | Establish individualized meal service program per 42 CFR § 418.100(j) and MCL § 333.21413(3)(g) |  | MCL § 333.21413(3)(g); 42 CFR § 418.100(j) | Consult dietary counselor; address therapeutic diets and patient food preferences
☐ | Comply with Michigan food service licensing requirements if food is prepared on-site |  | MCL § 289.4101 et seq. | Contact MDHHS Environmental Quality Division regarding on-site food service licensing
Phase 3 — Staffing for 24-Hour Residential Operations
☐ | Develop staffing plan ensuring 24-hour nursing services for each patient per their individual hospice care plan — ABSOLUTE legal requirement under MCL § 333.21413(3)(a) |  | MCL § 333.21413(3)(a) | 24-hour nursing services means nursing available throughout the 24-hour period per each patient's plan — not merely on-call
☐ | Hire sufficient RNs, LPNs, and hospice aides to maintain 24-hour coverage across all shifts and all patient beds |  | MCL § 333.21413(3)(a); R 325.45211 | Budget for 3 shifts daily plus call-out coverage
☐ | Develop and train all staff on the unconditional visitor access policy — patients MUST be permitted to receive visitors at any hour, including young children. No restrictions are permissible. |  | MCL § 333.21413(3)(f) | This is a binding legal obligation — document training in all staff personnel files
☐ | Complete MWBC fingerprint-based background checks for all direct-access residential staff before they begin patient care |  | MCL § 333.20173a / 333.20173b | miltcpartnership.org — 1-877-718-5547; volunteers with direct access in residential settings may also require MWBC checks
☐ | Develop infection control plan including explicit isolation procedures for patients with infectious diseases per MCL § 333.21413(3)(b) |  | MCL § 333.21413(3)(b) | Michigan requires specific isolation provisions — more stringent than federal CoP
Phase 4 — Michigan Hospice Residence License Application
☐ | Confirm eligibility: verify 2-year hospice licensure and compliance requirement is met with BCHS before submitting application |  | MCL § 333.21413(2) | (517) 241-0092 — LARA-BSCSupport@michigan.gov
☐ | Draft all policies specific to residence operations: 24-hour nursing, visitor access, infection isolation, food service, nurse call, medication management per MCL § 333.21413(3) |  | R 325.45301–R 325.45385
☐ | Obtain BFS fire safety approval documentation to include with application |  | MCL § 333.21413(3)(c) | BFS approval letter required as part of license application
☐ | ⚠ MI-SLS TRANSITION: No applications accepted after July 31, 2026, until MI-SLS launches (~August 19, 2026). All licenses not renewed by September 1, 2026 will be CLOSED. |  | LARA MI-SLS Transition Notice | Monitor michigan.gov/lara and mhha.org for MI-SLS instructions
☐ | Submit Michigan hospice residence license application through MI-SLS (formerly MiPLUS); include all required documents and application fee |  | R 325.45301 et seq.; milicensing.michigan.gov (transitioning to MI-SLS) | Fee non-refundable; confirm current amount with LARA
☐ | Schedule and complete BCHS facility inspection of the residence |  | LARA-BSCSupport@michigan.gov | BCHS will conduct on-site inspection before issuing residence license
☐ | Receive Michigan hospice residence license; confirm number of licensed beds, effective date, and any conditions |  | MCL § 333.20101 et seq. | Retain original; post as required; confirm new license number in MI-SLS
Phase 5 — Medicare & Medicaid Updates for the Residence
☐ | Update CMS-855A in PECOS to reflect the hospice residence as an additional practice location |  | pecos.cms.hhs.gov | Report change within 90 days; new location inspection may be triggered
☐ | Update Michigan Medicaid enrollment in CHAMPS to reflect hospice residence as a new place of service |  | milogintp.michigan.gov; ProviderSupport@Michigan.gov | Medicaid claims for residence patients must use 'Hospice Residence' as place of service
☐ | Train billing staff on CHAMPS admission/discharge process for hospice residence place of service |  | MDHHS MCC — michigan.gov/medicaidproviders | Timely CHAMPS entry required for correct PET/Benefit Plan assignment
☐ | Confirm room and board billing: residence room and board at home-care level is included in the hospice per diem — NOT billed at 95% NF rate |  | MDHHS Provider Manual, Hospice Chapter | Consult ProviderSupport@Michigan.gov for current billing guidance for hospice residences
Phase 6 — Pre-Opening Final Checks
☐ | Confirm BFS fire safety approval AND CMS/LSC compliance are documented; confirm BCHS residence license is active before admitting first patient |  | MCL § 333.21413(3)(c) | All three must be in hand — do not open without all approvals
☐ | Test all nurse call devices in every patient room; confirm devices are operational and within patient reach |  | MCL § 333.21413(3)(d)
☐ | Test fire alarm, sprinkler, emergency lighting, and evacuation systems; document test results |  | NFPA 101
☐ | Conduct residential Emergency Preparedness tabletop exercise with all residential staff; include fire evacuation and shelter-in-place scenarios |  | 42 CFR § 418.113
☐ | Conduct staff training on unconditional visitor access policy (MCL § 333.21413(3)(f)) — no exceptions, including young children — document in all personnel files |  | MCL § 333.21413(3)(f)
☐ | Complete infection control training for all residential staff, including isolation procedures per MCL § 333.21413(3)(b) |  | MCL § 333.21413(3)(b)
☐ | Conduct mock admission using full residential admission packet: election statement, patient rights, NPP, advance directive information, medication disposal policy |  | 42 CFR § 418.52; 42 CFR § 418.24
☐ | Update all public-facing materials, website, and marketing to reflect the hospice residence

## Changing the Location
Checklist 3: Changing the Location of a Michigan Hospice Agency
Michigan HomeCare and Hospice Association (MHHA) ¦ mhha.org ¦ 2026 Edition
ℹ Use this checklist when relocating the primary administrative office of an existing Michigan-licensed, Medicare-certified hospice agency. Complete notifications in the order listed — State of Michigan FIRST, then CMS, then Medicaid, then partners.
⚠ Do NOT submit an address change to CMS before notifying LARA/BCHS. Michigan requires the state to be notified first. Submitting to CMS first can create conflicting records and delay both updates.
✓ | Task / Action Required | Responsible Party | Regulatory Reference | Notes / Contacts | Date Completed
Phase 1 — Pre-Move Planning (Complete Before Moving)
☐ | Confirm new location is zoned for hospice agency administrative operations (zoning verification) |  |  | Some municipalities restrict healthcare administrative offices in residential zones
☐ | Confirm new location is within or compatible with your currently licensed Michigan service area; if moving to a new county, a service area amendment is also required |  | R 325.45121 | Contact BCHS before signing a lease: (517) 241-0092
☐ | Review lease or purchase agreement for terms consistent with healthcare facility requirements (accessibility, signage, parking)
☐ | Assess IT infrastructure at new location: network connectivity, EMR/EHR access, HIPAA security requirements |  | 45 CFR §§ 164.310–164.312 | Ensure ePHI safeguards are in place from day one at new location
☐ | Develop a move timeline that ensures continuous 24/7 hospice operations during transition — services must not be interrupted |  | 42 CFR § 418.100 | Patients must continue to receive all required services without disruption
☐ | Notify all staff of new address; update on-call coverage and clinical scheduling to account for move logistics
Phase 2 — Notify LARA/BCHS First (State of Michigan)
☐ | Notify LARA/BCHS of the address change through MI-SLS (formerly MiPLUS — milicensing.michigan.gov); confirm notification timing requirements before the move |  | (517) 241-0092 — LARA-BSCSupport@michigan.gov | ⚠ DO THIS FIRST — state must be notified before CMS
☐ | ⚠ MI-SLS TRANSITION: No change requests accepted after July 31, 2026, until MI-SLS launches (~August 19, 2026). Plan all pending change requests accordingly. |  | LARA MI-SLS Transition Notice | Monitor michigan.gov/lara and mhha.org for MI-SLS instructions
☐ | Submit updated agency information to BCHS: new physical address, mailing address (if different), and contact information |  | R 325.45111; milicensing.michigan.gov (transitioning to MI-SLS)
☐ | If new location changes your service area (new county), submit service area amendment and await BCHS approval before providing services in new county |  | R 325.45121 | Service area expansion requires prior BCHS approval
☐ | Confirm updated Michigan hospice license reflecting the new address has been issued; retain and post at new location |  | MCL § 333.20101 et seq. | Do not display an outdated license at new location; confirm new license number in MI-SLS
☐ | Update Michigan corporate/business records if address change also affects registered agent address, principal office address in Articles of Incorporation, or other corporate filings |  | Michigan Business Registry — mibusinessregistry.lara.state.mi.us | File Articles of Amendment or updated annual report as applicable
Phase 3 — Update CMS Federal Enrollment (PECOS)
☐ | Update practice location address on CMS-855A through PECOS at pecos.cms.hhs.gov |  | 42 CFR § 424.516; pecos.cms.hhs.gov | Report practice location changes within 90 days of the change
☐ | Update correspondence/mailing address in PECOS if different from practice location |  | pecos.cms.hhs.gov
☐ | Confirm with NGS Administrators (MAC) that remittance advices and paper correspondence will be sent to new address |  | ngsmedicare.com | Failure to update can result in missed payment notifications
☐ | Verify NPI record in NPPES reflects the updated address; update NPPES if needed |  | nppes.cms.hhs.gov — npiregistry.cms.hhs.gov | Some payers cross-reference NPI registry for address verification
☐ | Confirm DEA registration reflects correct agency address; update at deadiversion.usdoj.gov if needed |  | 21 CFR § 1301.51; dea.gov | DEA address must match actual location where controlled substances are stored or dispensed
Phase 4 — Update Michigan Medicaid (CHAMPS)
☐ | Update provider address and contact information in CHAMPS through MILogin |  | milogintp.michigan.gov | Contact ProviderSupport@Michigan.gov or 1-800-292-2550 if CHAMPS update assistance is needed
☐ | Confirm all Medicaid remittance advices and correspondence will be directed to new address |  | MDHHS
☐ | Confirm claims continue to process correctly after the update |  | ProviderSupport@Michigan.gov
Phase 5 — Update Michigan MAPS & Other State Programs
☐ | Update agency's Michigan MAPS registration to reflect new address |  | michigan.gov/maps
☐ | Update MWBC facility access credentials and facility address at miltcpartnership.org if needed |  | miltcpartnership.org — 1-877-718-5547
☐ | Notify Michigan Board of Nursing, Board of Social Work, Board of Medicine, and Board of Pharmacy of new agency address if required by any institutional licenses |  | michigan.gov/lara | Typically applies to institutional licenses, not individual professional licenses
Phase 6 — Update Accreditation (If Applicable)
☐ | Notify accrediting organization (CHAP, ACHC, or TJC) of address change per accreditation agreement terms |  | chapinc.org / achc.org / jointcommission.org | Some accreditors require on-site visit to new location before updating accreditation records
☐ | Confirm whether a new on-site inspection of the administrative location is required by your accreditor |  | Contact accreditor's account representative
Phase 7 — Update Internal Records, Partners & Payers
☐ | Update all internal policies and procedures that reference the agency's address
☐ | Update governing body records, organizational chart, and board resolutions to reflect new address
☐ | Update Emergency Preparedness Plan: new office location, updated evacuation routes, new local emergency management contacts |  | 42 CFR § 418.113 | Coordinate with local emergency management at new location
☐ | Notify all contracted nursing facilities, hospitals, pharmacies, DME vendors, ambulance services, and partner facilities of new address |  |  | Update written agreements if they reference the prior address
☐ | Update all managed care and Medicaid managed care plan contracts with new address
☐ | Update all patient/family communications, admission packets, and patient-facing materials |  | 42 CFR § 418.52
☐ | Update agency website, Google Business profile, referral source directories, and marketing materials
☐ | Update all staff contact information, business cards, email signatures, and letterhead
☐ | Update HIPAA Notice of Privacy Practices if agency address appears in NPP; distribute to all current patients |  | 45 CFR § 164.520 | Distribute at next patient contact or by mail
☐ | Execute updated HIPAA Business Associate Agreements with any vendors where physical address is referenced |  | 45 CFR § 164.504(e)
Phase 8 — Post-Move Confirmation
☐ | Confirm updated Michigan hospice license is displayed at new location |  | MCL § 333.20101 et seq.
☐ | Confirm updated PECOS enrollment reflects new address; verify through PECOS portal |  | pecos.cms.hhs.gov
☐ | Confirm CHAMPS reflects the new address; run test eligibility verification to confirm system is operating correctly |  | milogintp.michigan.gov
☐ | Conduct post-move staff walkthrough: confirm all operational systems (EMR, phones, on-call, fax) are fully functional
☐ | Confirm DEA and MAPS registrations reflect the correct new address
☐ | Confirm no patient services were interrupted during the move; review on-call logs and any patient complaints during transition |  | 42 CFR § 418.100
☐ | Update MHHA membership directory record to reflect new address |  | mhha.org